## WF1 - Order
Workflow 1: Customer Places an Order with a Restaurant
Project | ROS — Restaurant One Solution
Team | Data Mavericks
Date | 2026-06-20
Tested By | Challa Niharika
Test Case ID | What Was Tested | Input / Scenario | Expected Result | Actual Result | Pass / Fail | Bug Found | Fix Applied | Final Status
TC-01 | Restaurant profile database ingestion | Master_Restaurants.csv contains trailing spaces in text fields. | Load data cleanly with trimmed, uniform string column schemas. | Data loaded but threw formatting errors down the line. | Fail | Trailing whitespaces in string fields caused downstream node mismatches. | Added a String Manipulation node right after the reader using strip($restaurant_name$) to sanitize inputs. | Pass PDF
TC-02 | Seating capacity type configuration | Numeric capacity values ≤50 | Rule Engine appends profile category string "Boutique/Express". | Assigned category label perfectly. | Pass PDF | None | N/A | Pass
TC-03 | Profile boundary condition | Capacity value equals 0 seats | Rule Engine catches exception, appends "Unclassified/Review". | Handled anomalous bound correctly. | Pass PDF | None | N/A | Pass
TC-04
TC-05
TC-06
TC-07
TC-08
Total test cases | 3
Bugs found | 1
Bugs fixed | 1
Final status of workflow | Operational

## WF2 - Delivery
Workflow 2: Delivery Partner Delivers the Order
Project | ROS — Restaurant One Solution
Team | Data Mavericks
Date | 2026-06-20
Tested By | Sanjana Jaiswal
Test Case ID | What Was Tested | Input / Scenario | Expected Result | Actual Result | Pass / Fail | Bug Found | Fix Applied | Final Status
TC-01 | Multi-location date sorting keys | Join Orders & Deliveries datasets. | Complete 1-to-1 record map matching corresponding days. | Massively inflated row count (Data Explosion). | Fail | Joiner was configured only on restaurant_id, causing a massive Cartesian product duplicate row explosion. | Reconfigured the Joiner node to use a composite key pairing: restaurant_id AND order_date = delivery_date. | Pass
TC-02 | Automated variance math engine | Order amount equals external delivery API log values. | Math calculation column ($order_amount$ - $api_amount$) equals 0. | Column populated exact zero balances. | Pass | None | N/A | Pass
TC-03 | Discrepancy flagging logic | Order amount deviates from API value. | Tag rows with an "Unmatched" state flag. | Row marked as "Unmatched" for audit. | Pass | None | N/A | Pass
TC-04
TC-05
TC-06
TC-07
TC-08
Total test cases | 3
Bugs found | 1
Bugs fixed | 1
Final status of workflow | Operational

## WF3 - Cash-Up Published
Workflow 3: Cash-Up Published to the Finance Team
Project | ROS — Restaurant One Solution
Team | Data Mavericks
Date | 2026-06-20
Tested By | M.V.S.Harshith
Test Case ID | What Was Tested | Input / Scenario | Expected Result | Actual Result | Pass / Fail | Bug Found | Fix Applied | Final Status
TC-01 | Multi-source table chaining | Cascade merge of Cash_Up, Sales, and Expenses tables via ID. | All operational fields align correctly across shared dates. | Tables linked into unified schema safely. | Pass | None | N/A | Pass
TC-02 | Multi-variable arithmetic calculation | Processing formulas with varying costs, regional sales, and tax fields. | Compute precise EOD balance: $bod_amount$ + $sales$ - $expenses$ - $tax$ - $delivery_charges$ | EOD balances matched target arithmetic totals exactly. | Pass | None | N/A | Pass
TC-03 | Reconciliation status assignment | EOD variance balances equate to zero precisely. | Rule Engine tags record string parameter as "Reconciled". | Successfully flagged rows as "Reconciled". | Pass | None | N/A | Pass
TC-04
TC-05
TC-06
TC-07
TC-08
Total test cases | 3
Bugs found | 0
Bugs fixed | 0
Final status of workflow | Operational

## WF4 - Banking
Workflow 4: Cash-Up Amount Banked by the Designated Employee
Project | ROS — Restaurant One Solution
Team | Data Mavericks
Date | 2026-06-20
Tested By | M.G.Varshini
Test Case ID | What Was Tested | Input / Scenario | Expected Result | Actual Result | Pass / Fail | Bug Found | Fix Applied | Final Status
TC-01 | Bank lodge variance calculation | Compare physical bank lodgments to system eod_amount expectations. | Subtract expected cash from banked cash to yield variance. | Node threw "Invalid settings: No such column" error. | Fail | Column name mismatch error; the formula used a guessed variable $banked_amount$ instead of the actual file header string $banked_total$. | Opened the node settings dialog, wiped out the text string, and double-clicked the verified column token $banked_total$ - $eod_amount$. | Pass
TC-02 | Unreconciled exception gate routing | match_status flag equals 0 (Unreconciled). | Bypass standard rules; route text flag to "Exception (Unreconciled)". | Bypassed standard rule to allow deposit. | Pass | None | N/A | Pass
TC-03 | Lodge deficit evaluation | Deposit variance column contains negative balance parameters. | Rule Engine triggers automated label assignment: "Shortfall". | Tagged underpayments as "Shortfall". | Pass | None | N/A | Pass
TC-04
TC-05
TC-06
TC-07
TC-08
Total test cases | 3
Bugs found | 1
Bugs fixed | 1
Final status of workflow | Operational

## WF5 - Subscription
Workflow 5: Clients Purchase a Subscription with ROS
Project | ROS — Restaurant One Solution
Team | Data Mavericks
Date | 2026-06-20
Tested By | K.Partha Sarathi
Test Case ID | What Was Tested | Input / Scenario | Expected Result | Actual Result | Pass / Fail | Bug Found | Fix Applied | Final Status
TC-01 | Three-way relational cross join | Link core Client master file, Subscriptions bought, and Portal Users. | Pull client text names safely instead of raw key IDs. | Successfully merged business titles. | Pass | None | N/A | Pass
TC-02 | Active license profiling | Subscription flag attribute column equals 1. | Rule Engine tags user license status column as "Active". | Status column appended "Active" values. | Pass | None | N/A | Pass
TC-03 | GroupBy compression integrity | Apply multi-column aggregation formatting over matching client names. | Compress user detail repetitions; use a Sum function on Costs. | Rows flattened perfectly; sum was completely accurate. | Pass | None | N/A | Pass
TC-04
TC-05
TC-06
TC-07
TC-08
Total test cases | 3
Bugs found | 0
Bugs fixed | 0
Final status of workflow | Operational

## Overall Summary
ROS Project — Overall Testing Summary
Project | ROS — Restaurant One Solution
Team | Data Mavericks
Date | 2026-06-20
Tested By | Niharika, Sanjana, Harshith, Varshini, Partha Sarathi
Total test cases run | 15
Total bugs found | 3
Total bugs fixed | 3
Workflows fully passing (of 5) | 5
Overall conclusion | Implementation validation phases revealed a total of 3 operational processing defects across text string formats, relational key configurations, and header field assignments. Following customized node updates and iterative regression validation execution, 100% of the encountered defects have been successfully fixed and verified. The end-to-end framework fully passes all integrity checks and is declared completely production-ready.

## Column Guide
Column Meanings (Reference)
Column | What you write
Test Case ID | A label for the test (e.g. TC-01).
What Was Tested | The specific thing checked (e.g. UK tax calculation for a dine-in order).
Input / Scenario | The data or situation used for the test.
Expected Result | What should happen, according to the rules / logic.
Actual Result | What actually happened when the test was run.
Pass / Fail | Whether the actual result matched the expected result.
Bug Found | If it failed, what was wrong.
Fix Applied | How the problem was corrected.
Final Status | The result after fixing and re-testing.